## Team Roster
Sprint Vision: | Actividad 12
Sprint Team | Name | Alias | Primary Phone | Mobile Phone | Alternate Email | Instant Messaging
| Diego | DIE | - | - | diego@equipo.com | Teams
| Irma | IRM | - | - | irma@equipo.com | Teams
| Integrante 3 | INT3 | - | - | int3@equipo.com | Teams
| Integrante 4 | INT4 | - | - | int4@equipo.com | Teams
| Scrum Master | SM | - | - | sm@equipo.com | Teams
| Product Owner | PO | - | - | po@equipo.com | Teams
| Cesar | Cesar | Phone | Mobile | Alt Email | IM Information
| Unassigned | Unassigned | Phone | Mobile | Alt Email | IM Information
| Unassigned | Unassigned | Phone | Mobile | Alt Email | IM Information

## Capacity
Current Date |  | Fri | 2026-05-01
Sprint Start Date |  | Fri | 2026-05-01
Sprint Tracking Statistics
Productive Hours = | 8 |  | Sprint Days = | 12 |  | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-05-18
|  |  | Scrum Team | %age of time on Project | Assigned Hours | F | M | T | W | T | F | M | T | W | T | F | M |  |  | Available Hours
Total Remaining Hours: | 340 |  | DIE | 100% | 80 | 1 | 1 | 1 | 1 | 1 | 8 | 8 | 1 | 1 | 1 | 1 | 1 |  |  | 80
Total Capacity in Hours: | 340 |  | IRM | 100% | 80 | 1 | 1 | 1 | 1 | 1 | 8 | 8 | 1 | 1 | 1 | 1 | 1 |  |  | 80
Variance in Hours: | 0 |  | INT3 | 75% | 60 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 1 | 1 | 1 | 1 | 1 |  |  | 60
|  |  | INT4 | 75% | 60 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 1 | 1 | 1 | 1 | 1 |  |  | 60
|  |  | SM | 50% | 40 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 1 | 1 | 1 | 1 | 1 |  |  | 40
|  |  | PO | 25% | 20 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 1 |  |  | 20
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 |  |  | 0
[6 empty] | v | = | Vacation & Public Holiday | [5 empty] | h | = | OOF (Sick, Biz Travel etc.)

## Project Specific Reports
Work Type Breakdown
Feature | 9 | 75%
Tax | 2 | 16.67%
Precondition | 0 | 0%
Spike | 1 | 8.333%
Total | 12 | 100%
Functional Breakdown
Actividad 12 / Diccionario | 1 | 8.333%
Lectura de archivo | 2 | 16.67%
Búsqueda de tokens | 3 | 25%
Pruebas | 2 | 16.67%
Documentación | 2 | 16.67%
Revisión Scrum | 2 | 16.67%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
Total | 12 | 100%
Work Item Status | Cantidad | Porcentaje
Complete | 12 | 100%
In Progress | 0 | 0%
Pending | 0 | 0%
Postponed | 0 | 0%
Cancelled | 0 | 0%
Total | 12 | 100%

## Sprint
[5 empty] | Start Date | 2026-05-01 |  |  | 2026-05-01 |  |  | 2026-05-04 |  |  | 2026-05-05 |  |  | 2026-05-06 |  |  | 2026-05-07 |  |  | 2026-05-08 |  |  | 2026-05-11 |  |  | 2026-05-12 |  |  | 2026-05-13 |  |  | 2026-05-14 |  |  | 2026-05-15 |  |  | 2026-05-18 |  |  | 2026-05-19 |  | 2026-05-20 |  | 2026-05-21 |  |  | 2026-05-22 |  |  | 2026-05-25 |  |  | 2026-05-26 |  |  | 2026-05-27 |  |  | 2026-05-28 |  |  | 2026-05-29 |  |  | 2026-06-01 |  |  | 2026-06-02 |  |  | 2026-06-03
[9 empty] | Day 1 |  |  | Day 2 |  |  | Day 3 |  |  | Day 4 |  |  | Day 5 |  |  | Day 6 |  |  | Day 7 |  |  | Day 8 |  |  | Day 9 |  |  | Day 10 |  |  | Day 11 |  |  | Day 12 |  |  |  | Day 13 |  | Day 14 |  | Day 31 |  |  | Day 32 |  |  | Day 33 |  |  | Day 34 |  |  | Day 35 |  |  | Day 36 |  |  | Day 37 |  |  | Day 38 |  |  | Day 39 |  |  | Day 40
Worktype | Deliverable Area | Product Backlog Item or Group | Work item ID | Sprint Work item Description | Driver | Status | Pri | Initial | Spent | Left | Estado | Spent | Left | Estado | Spent | Left | Estado | Spent | Left | Estado | Spent | Left | Estado | Spent | Left | Estado | Spent | Left | Estado | Spent | Left | Estado | Spent | Left | Estado | Spent | Left | Estado | Spent | Left | Estado | Spent | Left | Estado | Spent | Left | Spent | Left | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Spent | Left |  | Total Effort
Feature | Actividad 12 / Diccionario | Diccionario de tokens | A12-001 | Leer archivo diccionario generado en actividad anterior | DIE | Complete | 1 | 6 | 0.5 | 5.5 | In Progress | 0.2 | 5.3 | In Progress | 0.3 | 5 | In Progress | 0.3 | 4.7 | In Progress | 0.5 | 4.2 | In Progress | 0.5 | 3.7 | In Progress | 0.5 | 3.2 | In Progress | 0.6 | 2.6 | In Progress | 0.8 | 1.8 | In Progress | 0.8 | 1 | In Progress | 0.6 | 0.4 | In Progress | 0.4 | 0 | Complete |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Feature | Lectura de archivo | Diccionario de tokens | A12-002 | Validar formato index;key;numdocs;start | IRM | In Progress | 1 | 5 | 0.4 | 4.6 | In Progress | 0.2 | 4.4 | In Progress | 0.2 | 4.2 | In Progress | 0.3 | 3.9 | In Progress | 0.4 | 3.5 | In Progress | 0.4 | 3.1 | In Progress | 0.4 | 2.7 | In Progress | 0.6 | 2.1 | In Progress | 0.6 | 1.5 | In Progress | 0.7 | 0.8 | In Progress | 0.5 | 0.3 | In Progress | 0.3 | 0 | Complete |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Feature | Búsqueda de tokens | Diccionario de tokens | A12-003 | Implementar búsqueda por palabra exacta | DIE | In Progress | 1 | 8 | 0.6 | 7.4 | In Progress | 0.4 | 7 | In Progress | 0.3 | 6.7 | In Progress | 0.5 | 6.2 | In Progress | 0.6 | 5.6 | In Progress | 0.6 | 5 | In Progress | 0.7 | 4.3 | In Progress | 0.9 | 3.4 | In Progress | 1 | 2.4 | In Progress | 1.1 | 1.3 | In Progress | 0.8 | 0.5 | In Progress | 0.5 | 6.6613e-16 | Complete |  | 6.6613e-16 |  | 6.6613e-16 |  | 6.6613e-16 |  |  | 6.6613e-16 |  |  | 6.6613e-16 |  |  | 6.6613e-16 |  |  | 6.6613e-16 |  |  | 6.6613e-16 |  |  | 6.6613e-16 |  |  | 6.6613e-16 |  |  | 6.6613e-16 |  |  | 6.6613e-16
Feature | Búsqueda de tokens | Diccionario de tokens | A12-004 | Implementar cálculo/hash para localizar índice | INT3 | In Progress | 1 | 8 | 0.6 | 7.4 | In Progress | 0.4 | 7 | In Progress | 0.3 | 6.7 | In Progress | 0.5 | 6.2 | In Progress | 0.6 | 5.6 | In Progress | 0.6 | 5 | In Progress | 0.7 | 4.3 | In Progress | 0.9 | 3.4 | In Progress | 1 | 2.4 | In Progress | 1.1 | 1.3 | In Progress | 0.8 | 0.5 | In Progress | 0.5 | 6.6613e-16 | Complete |  | 6.6613e-16 |  | 6.6613e-16 |  | 6.6613e-16 |  |  | 6.6613e-16 |  |  | 6.6613e-16 |  |  | 6.6613e-16 |  |  | 6.6613e-16 |  |  | 6.6613e-16 |  |  | 6.6613e-16 |  |  | 6.6613e-16 |  |  | 6.6613e-16 |  |  | 6.6613e-16
Feature | Búsqueda de tokens | Diccionario de tokens | A12-005 | Mostrar numdocs y posición start del token encontrado | INT4 | In Progress | 1 | 6 | 0.5 | 5.5 | In Progress | 0.2 | 5.3 | In Progress | 0.3 | 5 | In Progress | 0.3 | 4.7 | In Progress | 0.5 | 4.2 | In Progress | 0.5 | 3.7 | In Progress | 0.5 | 3.2 | In Progress | 0.6 | 2.6 | In Progress | 0.8 | 1.8 | In Progress | 0.8 | 1 | In Progress | 0.6 | 0.4 | In Progress | 0.4 | 0 | Complete |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Feature | Pruebas | Diccionario de tokens | A12-006 | Probar búsqueda con palabras existentes | IRM | In Progress | 2 | 5 | 0.4 | 4.6 | In Progress | 0.2 | 4.4 | In Progress | 0.2 | 4.2 | In Progress | 0.3 | 3.9 | In Progress | 0.4 | 3.5 | In Progress | 0.4 | 3.1 | In Progress | 0.4 | 2.7 | In Progress | 0.6 | 2.1 | In Progress | 0.6 | 1.5 | In Progress | 0.7 | 0.8 | In Progress | 0.5 | 0.3 | In Progress | 0.3 | 0 | Complete |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Feature | Pruebas | Diccionario de tokens | A12-007 | Probar búsqueda con palabras inexistentes | INT3 | In Progress | 2 | 4 | 0.3 | 3.7 | In Progress | 0.2 | 3.5 | In Progress | 0.1 | 3.4 | In Progress | 0.3 | 3.1 | In Progress | 0.3 | 2.8 | In Progress | 0.3 | 2.5 | In Progress | 0.3 | 2.2 | In Progress | 0.5 | 1.7 | In Progress | 0.5 | 1.2 | In Progress | 0.6 | 0.6 | In Progress | 0.4 | 0.2 | In Progress | 0.2 | 6.1062e-16 | Complete |  | 6.1062e-16 |  | 6.1062e-16 |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16
Tax | Documentación | Entrega | A12-008 | Documentar uso del programa y capturas de ejecución | IRM | In Progress | 2 | 5 | 0.4 | 4.6 | In Progress | 0.2 | 4.4 | In Progress | 0.2 | 4.2 | In Progress | 0.3 | 3.9 | In Progress | 0.4 | 3.5 | In Progress | 0.4 | 3.1 | In Progress | 0.4 | 2.7 | In Progress | 0.6 | 2.1 | In Progress | 0.6 | 1.5 | In Progress | 0.7 | 0.8 | In Progress | 0.5 | 0.3 | In Progress | 0.3 | 4.996e-16 | Complete |  | 4.996e-16 |  | 4.996e-16 |  | 4.996e-16 |  |  | 4.996e-16 |  |  | 4.996e-16 |  |  | 4.996e-16 |  |  | 4.996e-16 |  |  | 4.996e-16 |  |  | 4.996e-16 |  |  | 4.996e-16 |  |  | 4.996e-16 |  |  | 4.996e-16
Spike | Lectura de archivo | Diccionario de tokens | A12-009 | Revisar manejo de errores de archivo no encontrado | DIE | In Progress | 2 | 4 | 0.3 | 3.7 | In Progress | 0.2 | 3.5 | In Progress | 0.1 | 3.4 | In Progress | 0.3 | 3.1 | In Progress | 0.3 | 2.8 | In Progress | 0.3 | 2.5 | In Progress | 0.3 | 2.2 | In Progress | 0.5 | 1.7 | In Progress | 0.5 | 1.2 | In Progress | 0.6 | 0.6 | In Progress | 0.4 | 0.2 | In Progress | 0.2 | 6.1062e-16 | Complete |  | 6.1062e-16 |  | 6.1062e-16 |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16
Feature | Revisión Scrum | Scrum | A12-010 | Actualizar plantilla con 11 sprints concluidos | SM | In Progress | 1 | 6 | 0.5 | 5.5 | In Progress | 0.2 | 5.3 | In Progress | 0.3 | 5 | In Progress | 0.3 | 4.7 | In Progress | 0.5 | 4.2 | In Progress | 0.5 | 3.7 | In Progress | 0.5 | 3.2 | In Progress | 0.6 | 2.6 | In Progress | 0.8 | 1.8 | In Progress | 0.8 | 1 | In Progress | 0.6 | 0.4 | In Progress | 0.4 | 0 | Complete |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Feature | Revisión Scrum | Scrum | A12-011 | Agregar sprint actual de Actividad 12 | SM | In Progress | 1 | 6 | 0.5 | 5.5 | In Progress | 0.2 | 5.3 | In Progress | 0.3 | 5 | In Progress | 0.3 | 4.7 | In Progress | 0.5 | 4.2 | In Progress | 0.5 | 3.7 | In Progress | 0.5 | 3.2 | In Progress | 0.6 | 2.6 | In Progress | 0.8 | 1.8 | In Progress | 0.8 | 1 | In Progress | 0.6 | 0.4 | In Progress | 0.4 | 0 | Complete |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Tax | Documentación | Entrega | A12-012 | Identificar perfil del burn down chart | PO | In Progress | 1 | 4 | 0.3 | 3.7 | In Progress | 0.2 | 3.5 | In Progress | 0.1 | 3.4 | In Progress | 0.3 | 3.1 | In Progress | 0.3 | 2.8 | In Progress | 0.3 | 2.5 | In Progress | 0.3 | 2.2 | In Progress | 0.5 | 1.7 | In Progress | 0.5 | 1.2 | In Progress | 0.6 | 0.6 | In Progress | 0.4 | 0.2 | In Progress | 0.2 | 6.1062e-16 | Complete |  | 6.1062e-16 |  | 6.1062e-16 |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16 |  |  | 6.1062e-16
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[6 empty] | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
[49 empty] | 0 | 3.6637e-15 | 0 | 0 | 3.6637e-15 | 0 | 0 | 3.6637e-15 | 0 | 0 | 3.6637e-15 | 0 | 0 | 3.6637e-15 | 0 | 0 | 3.6637e-15 | 0 | 0 | 3.6637e-15 | 0 | 0 | 3.6637e-15 | 0 | 0 | 3.6637e-15 | 0 | 0 | 3.6637e-15 | 0
Formulas:
Status = (INDEX(Burndown,ROW([Status])-ROW(G3),MIN(TODAY()-SprintStart,29)*3+3))

## Sprint History
Sprint | Actividad / Entregable | Estado | Horas iniciales | Horas terminadas | Observaciones
1 | Actividad 1 | Concluido | 45 | 45 | Sprint cerrado
2 | Actividad 2 | Concluido | 50 | 50 | Sprint cerrado
3 | Actividad 3 | Concluido | 55 | 55 | Sprint cerrado
4 | Actividad 4 | Concluido | 40 | 40 | Sprint cerrado
5 | Actividad 5 | Concluido | 45 | 45 | Sprint cerrado
6 | Actividad 6 | Concluido | 50 | 50 | Sprint cerrado
7 | Actividad 7 | Concluido | 55 | 55 | Sprint cerrado
8 | Actividad 8 | Concluido | 40 | 40 | Sprint cerrado
9 | Actividad 9 | Concluido | 45 | 45 | Sprint cerrado
10 | Actividad 10 | Concluido | 50 | 50 | Sprint cerrado
11 | Actividad 11 | Concluido | 55 | 55 | Sprint cerrado
12 | Actividad 12 - Diccionario de tokens | Sprint actual mostrado | 67 | 67 | Perfil burn down: avance tardío / hockey stick